## Slide 1: Creating the Cutting Edge Conclave
Planning and Developing Conclave

## Slide 2: Learning Objectives
Explain the importance of, and how plan and develop a Conclave and all that it entails
Demonstrate how to plan specific areas of a Conclave program (i.e. activities, training, shows)
Guide brothers in the areas to focus on, the questions to ask, and where to go to get help
Enable Arrowmen to create a cutting edge Conclave that educates and inspires

## Slide 3: What is the purpose of conclave?
This training session is titled,
“Planning and Developing Conclave”
Let’s begin with a simple question…
What do we have to consider when planning and developing a conclave?

## Slide 4: Purpose
Provide a plethora of training opportunities to lodge leaders
Provide a forum for lodges to share ideas and best practices
Provide ideas and information on new programs developed by the Order
Provide lodge members to an opportunity to meet section, regional, and possibly national officers
Provide an opportunity for lodge officers and members to have fun and memorable weekend

## Slide 5: Planning
Start with a back-dater
  What are some important events or key planning dates that would be included on a back-dater?
Let's brainstorm the important milestones that need to be on our back-dater
Helpful hints:
  Regular communication (Communication Plan)
  Conclave promotion (Marketing and Promotional Toolkit)
  Develop and foster a “Conclave Culture” within the Section
  Define roles and expectations of Section Officers, Council of Chiefs, Conclave Vice Chiefs, and Service Lodge

## Slide 6: Conclave Roadmap
Months 0-4 (Conclave Sunday Business Meeting and 1st COC)
Sunday Business Meeting
  Elect new officers
  Conclave presentation (by upcoming service lodge)
  Basic promotions tool kit
1st COC
  Review last year’s conclave report (successes and lessons learned)
  Announce CVCs and Advisers
  Approve conclave budget
  Breakouts for CVCs (planning)
  Camp visitation
  Select conclave theme
  Establish fee Structure and any other administrative Items
  Get an estimate of attendance from each lodge regarding the upcoming conclave
  Full promotional tool kit (in addition to what was previous distributed)
  Newsletter articles, social media posts, etc.
  Perhaps buttons or other wearable promotional items
  Schedule lodge visitations by section offers to promote conclave at lodge events.
  Establish incentives, competition, scholarships to lodges in order to foster early registration and increased attendance

## Slide 7: Conclave Roadmap
Months 4-8 (2nd COC)
Confirmation from lodges regarding estimates on attendance (perhaps require this to be binding; you can always add up to a certain point, such as 2 weeks prior to the event)
Vote on conclave logo and other trading post items
Reports and breakouts by CVCs and the service lodge
  Service lodge: Menu, amenities, special needs, and other relevant planning information
  Training: identify core trainers and cells
  Shows: outline of shows
  Activities: outline of events
  AIA: outline of AIA
  Other CVCs/Committees: outlines
New promotional tool kit items (i.e., keeping it fresh)
  Check-in with lodges regarding interest and promotions (identify weak points)

## Slide 8: Conclave Roadmap
Months 8-12 (3rd COC – Count Down to Conclave)
Final reports from CVCs, service lodge, and COC. This intended to be a check-in with all of the heavy lifting occurring prior to this date
Identify final action items, travel plans, etc.

## Slide 9: Scheduling
Conclave Schedule
Let's brainstorm important events that need to be on our schedule
  While you may think your section’s schedule is set, it probably isn’t and changes can bring new life to a conclave
  So what occurs Friday night? Saturday? Sunday?

## Slide 10: Program
The key sections of conclave program
  Training
  Activities
  Shows
There must be something for everyone!
  From the newest Arrowman to the oldest adviser…
Remember that program is the heart of the conclave

## Slide 11: Training
Training isn’t always the thing participants leave a conclave remembering, but it is the one thing that can help strengthen our lodges and build better leaders
Make sure the training sessions cover a wide variety of topics and knowledge levels
Overview of training programs to consider
  Open Sessions
  “University Style” Sessions
We will do a deep dive into conclave training in a separate session

## Slide 12: Activities
Some sections have a show on Friday night while some run activities then, and all sections have activities on Saturday afternoon
Sharing ideas and experiences
Group breakout topics:
  American Indian
  Camp-related (swimming, etc.)
  Game shows
  Food competitions
  Sports, lodge competitions, etc.

## Slide 13: Shows
This can be the most memorable part of the conclave or it can be the biggest flop
It can be a very simple show like a camporee would have or it can be as elaborate as a NOAC stage show
Provide the right kind of show for your audience
Do something different each year
What types of shows have you seen?

## Slide 14: W W W s of Logistics Planning
WATER
  Make Sure Potable (Drinking) Water is Safe (Tested & Heath Certified)
  Make Sure Drinking Water Is Available to Attendees During All Activities
WASTE
  Plan for Solid Waste Management and Disposal
  Sanitary Waste (Minimum of 3 Toilets Per 100 Attendees)
WELFARE (STAFF)
  Safety (Site Safety Inspections & Check-in Safety Brief)
  Telecommunications (Key Staff in “Real-time” by Radios/Smartphones)
  Alerts (Fire, Bad Weather, etc. with Instructions & Assembly Points)
  Food (Preparation/Serving, Food Kept Hot/Cold & Trained Preparers)
  First Aid Station

## Slide 15: Physical Disabilities Accommodations
Be Prepared and Endeavor So Far As in Your Power Lies, to Be Unselfish in the Service and Devotion to the Welfare of Others
When Planning your Conclave, Remember to Plan How to Accommodate Persons With Physical Disabilities, such as:
  Attendees in Wheelchairs
  Attendees Who Are Deaf
  Attendees Who Are Blind
Be Inclusive, NOT Exclusive
  Some Activities Will Be Exclusive to Attendees With Disabilities
  However, It Is NOT Difficult to Include Attendees with Disabilities at Conclaves if Accommodations Are Planned for in Advance

## Slide 16: Duty to God
Lord Baden-Powell once said: "The Scout, in his promise, undertakes to do his duty to his king and country only in the second place; his first duty is to GOD. It is with this idea before us and recognizing that GOD is the one Father of us all, that we Scouts count ourselves a brotherhood despite the difference among us of country, creed, or class.”
Remember to Include:
  An “Interfaith” Worship Service and Optional Faith-specific Worship Services Depending on Your Conclave’s Faith Demographics
  “Interfaith” Invocations/Benedictions at Opening/Closing Ceremonies
  “Interfaith” Prayers before Meals

## Slide 17: Summary
Conclave program areas: training, activities, and shows
New ideas to bring home to use at your upcoming conclave
Many different types of things you can do at a conclave
Provide a well-rounded program that is fun and engaging to everyone who is in attendance
If you do this, everyone will have a great time and it will be a conclave to remember

## Slide 19: For Training Resources and More Information Visit:
http://training.oa-bsa.org/noac2015